## Event Master
SL. No. | Date | Reporting / Registration Time | Event Timing | Venue | Event Type | TEAM Caps | Mid Evaluation | Format of In-person Event | Event Name | No. of Judges | Faculty Incharge | Student Leads | Number of Volunteers | Total Participants / Teams | Participation Fee | PRIZE | Category | Short Description | Technical Requirements | Physical / Venue Requirements | Registration Kit | Participant Verification Documents | Volunteer Needed – Categories | Evaluation / Judging Notes | Printable / Admin Documents | Status / Pending Items
1 | 2026-10-11 | 7:00 AM – 8:00 AM | 8:00 AM – 1:00 PM | Football Ground | Drone Obstacle Course | 1 - 3 | NO | Each team/indiviodual compete by flying their drones through set of obstacle courses and points allocated according to their skills , compleation time and other criterias | FALCON STRIKE | 3 | Sanjay Ray Santosh Sahu J Binita | PARTHA SARATHI NAYAK ADISAKTI SAHOO | 15 | 20 Teams | ₹500 per participant/team | 1st prize- 5000 , 2nd prize- 3000 , 3rd prize- 2000 TOTAL PRIZE POOL - 10000 | Drone / Robotics | Practical drone navigation competition testing precision, control, reaction time, navigation, technical understanding, stability and decision-making through a predefined obstacle course. | Technical inspection and calibration area; battery charging points; power supply where required. | Designated outdoor drone arena; safety barriers/perimeter; obstacle course with hoops, gates and elevation challenges; judges' observation stand; score recording desk/Boards So the judges can carry it around ; registration and evaluation desks. | Participant ID Card; Event Sticker | Aadhaar ID Card; College ID Card; Approval Letter; Selection / Confirmation Mail | Event Management; Technical & Network; Registration & Desk; Evaluation & Judging; Discipline & Safety, Obstacle Setup , Instructors for helping the participants understand rules and regulations | Detailed drone rules and scoring criteria are TBD. Final performance assessed by designated judges. | Event Registration Sheet; Selected Participant/Team List; Evaluation Sheets | Drone course layout and detailed rules/rubric pending finalization.
2 | 2026-10-11 | 8:00 AM - 9:00 AM | 10:00 AM - 1:00 PM | Auditorium, MBA Block | Inaguration | SOLO ( 1 ) |  |  | TBD | 0 |  |  | 10 | Open | ---- | NA | Ceremony | Official opening ceremony of the NIRMIT festival. | PA System, Mics, Projector | Stage setup, seating arrangement for VIPs | None | None | Hospitality, Crowd Management | N/A | Schedule, VIP Guest List | Guest confirmation pending
3 | 2026-10-11 | 8:00 AM - 9:00 AM | 10:00 AM – 1:00 PM | Academic Conference Hall | Technical Poster Presentation | 1 - 3 | YES ( Poster + Explanation in form ) | Each selected team / individual showcase their poster which they have made during their mid evaluation the topic is alrrady provided during mid evaluation and they will be judged on the basis of their proper explanation and other criterias in person | STARK EXPO | 3 |  | Ankeeta Mohanty , Priyabrata Muduli ( MBA ) | 5 | 20 Teams | ₹200 per team | 1st prize- 5000 , 2nd prize- 3000 , 3rd prize- 2000 TOTAL PRIZE POOL - 10000 | Branding & Desiging | Students present technical posters on innovative engineering topics. | Screens/ Projector / monitor for display , mics , laptop connection cords | Poster boards, pins, display area | Participant ID Card; Event Sticker | Aadhaar ID Card; College ID Card; Approval Letter; Selection / Confirmation Mail | Event Management, Evaluation & Judging | Evaluation based on content, design, and presentation. | Evaluation Sheets | Judges to be finalized
4 | 2026-10-11 | 8:00 AM - 9:00 AM | 10:00 AM - 1:00 PM | Reading Room, Central Library | Canvas Painting | SOLO ( 1 ) | NO | The theme / topic will be given on spot and the best drawing wins with following criterias | INFINITY CANVAS | 2 | Madhubrata Dash Sambit Sethy Swarnaprava Sahoo | Sanjeevani ( Btech ) , Shayan ( Diploma ) | 8 | Open ( Limit 100 ) | ₹200 per participant | 1st prize- 5000 , 2nd prize- 3000 , 3rd prize- 2000 TOTAL PRIZE POOL - 10000 | Art & Creativity | Creative canvas painting competition with a predefined theme. | TBD | Canvas board with sheet ( or isle stands ) 16x24, Painting Kit ( Optional ) | Canvas, Basic Colors, Stickers | Aadhaar ID Card; College ID Card; Approval Letter; Selection / Confirmation Mail | Event Management, Discipline & Safety | Evaluated on creativity, adherence to theme, and neatness. | Evaluation Sheets | Theme announcement pending
5 | 2026-10-11 | 12:00 PM – 1:00 PM | 2:00 PM - 5:00 PM | Electrical Block Hallway, NMIET | IoT Display | 1 - 3 | YES ( PPT + EXPLANATION + WORKING VIDEO IN FORM ) | The selected team / individuals will get chance to represet their innovation to panel of judges and evaluation will be done based upon set criterias | PROJECT ULTRON | 2026-03-02 | JITENDRA PADHI(8895781339) , BHAGYALAXMI DEVI (8249858397) , PRANAY ROUT(8249524153) | SUBHASREE PANDA VASWATI P MOHANTY JAGA DAS | 10 | 20 | ₹300 per participant | 1st prize- 5000 , 2nd prize- 3000 , 3rd prize- 2000 TOTAL PRIZE POOL - 10000 | IoT / Exhibition | Exhibition where participants showcase connected devices, sensors, automation and real-world IoT applications to judges, organizers and visitors. | Wi-Fi connectivity where cloud-connected demonstrations require it; power supply at each display station. | Exhibition space; display tables with dual power outlets per project station; display boards for project posters and technical specifications; venue/display-space coordination. | Participant ID Card; Event Sticker | Aadhaar ID Card; College ID Card; Approval Letter; Selection / Confirmation Mail | Event Management; Technical & Network; Registration & Desk; Evaluation & Judging; Marketing, Media & Design | Evaluation areas: innovation, technical implementation, practical application, functionality, UX, presentation, scalability & impact. Final rules, team size and full scoring criteria are TBD. | Event Registration Sheet; Selected Participant/Team List; Evaluation Sheets | Final team size and detailed scoring criteria pending finalization.
6 | 2026-10-11 | 1:00 PM - 2:00 PM | 3:00 PM - 5:00 PM | Auditorium, MBA Block | Panel Disscussion | SOLO ( 1 ) | NO |  | COUNCIL OF HEROES | 0 | Kashinath Pati, Sambit Sethi, Barsha Priyadarshinee | Sagar Nayak Puja Jena | 6 | Open | FREE | N/A | Discussion / Talk | Expert panel discussing current trends in technology and business. | Mics, PA System, Projector | Stage setup, Sofa seating for panelists | Notepad, Pen | None | Hospitality, Crowd Management | N/A | Guest List, Agenda | Panelists confirmation pending
7 | 2026-10-11 | 1:00 PM – 2:00 PM | 3:00 PM – 5:00 PM | Seminar Hall , MBA Block | AD Mad Show | TRIO ( 3 ) | NO | Teams receive a product or topic unexpectedly, get a short preparation window (5 to 15 minutes), and perform an ad live on stage. | THUNDERBOLTS | 3 | Subhasmita Mam • Nilima Mam |  | 5 | 15 Teams | ₹500 per team | 1st prize- 5000 , 2nd prize- 3000 , 3rd prize- 2000 TOTAL PRIZE POOL - 10000 | Branding & Desiging | Creative advertising competition where teams create quirky ads for given products. | Mics, Audio System | Stage, seating for audience | Participant ID Card | Aadhaar ID Card; College ID Card; Approval Letter; Selection / Confirmation Mail | Event Management, Crowd Management | Evaluated on humor, creativity, and product integration. | Evaluation Sheets, Product Chits | Product list to be finalized
8 | 2026-10-12 | 8:00 AM – 9:00 AM | 10:00 AM – 8:00 PM | Auditorium, MBA Block | Techno Dance | 5 - 10 | YES ( Dance video ) |  | GUARDIANS OF THE GROOVE | 3 | Saroj Sir Sushree Sucharita Kar | Rachita Das Subhranshu Sekhar Jena | 12 | 15 Teams ( 10 Mins ) | ₹1000 per Team ( Inter college - No cross college / Mng & eng students | 1st prize- 10000 , 2nd prize- 5000 , 3rd prize- 3000 TOTAL PRIZE POOL - 18000 | Cultural / Dance | High-energy dance competition featuring technology-themed performances. | High-quality Sound System, Lighting, Mics | Dance floor/stage, Green rooms | Participant ID Card, Stickers | Aadhaar ID Card; College ID Card; Approval Letter; Selection / Confirmation Mail | Event Management, Backstage, Crowd Management | Evaluated on choreography, energy, theme integration, and synchronization. | Evaluation Sheets | Lighting setup pending
9 | 2026-10-12 | 8:00 AM – 9:00 AM | 10:00 AM–01:00 PM | Seminar Hall, MBA Block | CXO Round Table | 4 - 5 | NO | Think like a leader, decide like a CXO Each team must consist of 4–5 members. Each participant will take on a specific C-suite role such as CEO, CTO, CMO, CFO, COO, etc. A case brief will be provided at the beginning of the challenge. Teams will have 15 minutes to analyze the case, discuss their strategy, and decide their approach. Each participant must contribute from the perspective of their assigned executive role. Teams must develop a strategy focused on growing and strengthening their company. Participants must not discuss the case with anyone outside their team during the preparation period. Each team will have a maximum of 5 minutes to present their final strategy. Every team member must speak during the final presentation. A host/moderator will manage the session and ensure time discipline. The judges’ decision will be final and binding. | SHIELD BOARDROOM | 0 | Akankhya Mam |  | 5 | 15 - 20 Teams | ₹500 per Team | 1st prize- 5000 , 2nd prize- 3000 , 3rd prize- 2000 TOTAL PRIZE POOL - 10000 | Business & Tech | Exclusive roundtable discussion with industry CXOs on future tech landscapes. | Mics, Projector, Video Conferencing Setup | Round table seating, premium hospitality | Welcome Kit, Notepad, Pen | Invitation Email | Hospitality, Protocol | N/A | Guest List, Name Tags | CXO confirmations pending
10 | 2026-10-12 | 8:00 AM - 9:00 AM | 10:00 AM - 12:00 PM | Reading Room, Central Library | Tech Biz Quiz | 1 - 2 | NO | participants will go through 3 stages....the one on top of leaderboard / point table wins | QUANTUMANIA | 1 | Chanchal Mukherjee , Neeha Pradhani , Sangram Behera | DIBYANSHU NAYAK ( 7077188155 ) TAPASWINI MISHRA ( 9861296488 ) | 6 | 30 Teams | ₹200 per Team | 1st prize- 5000 , 2nd prize- 3000 , 3rd prize- 2000 TOTAL PRIZE POOL - 10000 | Quiz | Trivia competition testing knowledge on latest technology, IT, and science. | Projector, Buzzer System, Mics | Stage for finalists, seating for audience | Participant ID Card, Stickers | Aadhaar ID Card; College ID Card; Approval Letter; Selection / Confirmation Mail | Event Management, Technical Support | Multiple rounds including MCQs, rapid-fire, and visual rounds. | Question Bank, Score Sheets | Question bank finalization
11 | 2026-10-12 | 12:00 PM – 1:00 PM | 1:00 PM – 5:00 PM | Seminar Hall, MBA Block | Ideathon | 2 - 5 | YES ( PPT + EXPLANATION + INTRO VIDEO IN FORM ) | The selected teams will get chance to pitch their ideas infront of panel of judges and based on their ideas & criterias the winning teams will be decided | MULTIVERSE OF IDEAS | 2026-05-03 | Jaswant |  | 10 | 20 - Per team total time - 12mins ( Pitch timing - 5-7mins max ) | ₹300 per Team | 1st prize- 5000 , 2nd prize- 3000 , 3rd prize- 2000 TOTAL PRIZE POOL - 10000 | Innovation / Ideation | Idea-focused challenge where participants identify a meaningful problem, understand users and propose a technology-driven solution within the session timeframe. | Presentation display/projection system; audio system; presentation clicker; timer display; power supply for judging/scoring devices. | Seminar Hall with adequate seating; podium; judging panel table; presentation area. | Participant ID Card; Event Sticker | Aadhaar ID Card; College ID Card; Approval Letter; Selection / Confirmation Mail | Event Management; Technical & Network; Registration & Desk; Evaluation & Judging; Marketing, Media & Design | Submission may include problem statement, target users, proposed solution, technology approach, UVP, expected impact, future scope and business/sustainability model. Criteria include relevance, innovation, feasibility, impact, technical potential, scalability, presentation and overall idea quality. | Event Registration Sheet; Selected Participant/Team List; Evaluation Sheets | Detailed Ideathon format, team size and judging rubric pending finalization.
12 | 2026-10-12 | 1:00 PM - 2:00 PM | 3:00 PM - 5:00 PM | Conference Hall, Academic Block | Seminar / Workshop | SOLO ( 1 ) | NO |  | MARVEL OF MINDS | 0 |  |  | 5 | Open | FREE | N/A | Seminar / Talk | Educational seminar delivered by industry experts on emerging technologies. | Projector, Mics, PA System | Auditorium seating, Podium | Notepad, Pen | None | Hospitality, Crowd Management | N/A | Attendance Sheet | Speaker confirmation pending
14 | 2026-10-13 | 9:00 AM - 10:00 AM | 10:00 AM - 12:00 PM | Conference Hall, Academic Block | Face Painting | DUO ( 2 ) | NO | The theme / topic will be given on spot and the best drawing wins with following criterias | ALTER EGO/ INFINITY FACES |  | Barsha Priyadarshini, Gopabandhu Sahu, Bhagyalaxmi Devi | Subhranshu , Swati | 10 |  | ₹200 per Team | 1st prize- 5000 , 2nd prize- 3000 , 3rd prize- 2000 TOTAL PRIZE POOL - 10000
15 | 2026-10-13 | 8:00 AM - 9:00 AM | 9:00 AM - 1:00 PM | Seminar Hall, MBA Block | Marketing Maverick | QUATRET ( 4 ) | NO | teams receive a real-world business problem, go-to-market (GTM) challenge, or consulting brief.Deliverable: A structured presentation deck (PPT/PDF) detailing market research, target audience segmentation, positioning, and data-driven solutions.Round 3: Grand Finale / Live PitchFormat: Finalist teams (usually top 8 to 10 teams) present their solutions live.Evaluation: A 10-minute presentation followed by a Q&A session judged by industry experts and senior faculty. | Battle of Brands | 3 | Nitin Sir • Subhasmita Mam |  | 6 | 20 Teams | ₹500 per Team | 1st prize- 5000 , 2nd prize- 3000 , 3rd prize- 2000 TOTAL PRIZE POOL - 10000 | Marketing & Business | Business challenge where teams pitch marketing strategies for given case studies. | Projector, Mics | Presentation area, seating for audience | Participant ID Card, Stickers | Aadhaar ID Card; College ID Card; Approval Letter; Selection / Confirmation Mail | Event Management, Registration | Evaluated on strategy, feasibility, creativity, and presentation skills. | Evaluation Sheets, Case Studies | Case studies to be finalized
16 | 2026-10-13 | 1:30 PM – 2:00 PM | 3:00 PM – 5:00 PM | Auditorium, MBA Block | Free Fire Gaming Tournament | QUATRET ( 4 ) | NO | Total 24 teams.....Room A will have 12 teams competeing live and Room B will have 12 teams competeing....top 3 from both matches based on point table will be selected for another match. Room C ( Final round ) Top 6 teams compete to Win. | CIVIL WARS | - | RASHMI RANJAN RATH , OM PRAKASH NARAYAN KAR , PRABIR DAS | SUKDEV SUNA SUBHAM SING | 8 | 24 teams maximum | ₹400 per Team | 1st prize- 5000 , 2nd prize- 3000 , 3rd prize- 2000 TOTAL PRIZE POOL - 10000 | Gaming / Esports | Competitive esports tournament focused on team coordination, strategy, decision-making, communication and competitive gaming skills. | Stable high-speed / low-latency Wi-Fi or Internet; dedicated power supply; technical support; gaming infrastructure; match administration and technical supervision. | Air-conditioned auditorium; ergonomic tables and chairs; device charging strips; large display screens/monitors for spectators. ( SAME SETUP AS HACKATHON ) | Participant ID Card; Gaming Sticker; Finger gloves (where applicable) | Aadhaar ID Card; College ID Card; Approval Letter; Selection / Confirmation Mail | Event Management; Technical & Network; Registration & Desk; Evaluation & Judging; Discipline & Safety, Obstacle Setup , Instructors for helping the participants understand rules and regulations | Room A and Room B feed into Grand Final. Exact advancement, match format, team composition, device requirements, scoring and anti-cheating rules are TBD. | Event Registration Sheet; Selected Team List; Evaluation Sheets | Official gaming rulebook pending finalization.
17 | 14 – 15 October 2026 | 8:00 AM on 10 October 2026 | Day 1: 8:00 AM launch; 2:00 PM – 6:00 PM Mid Evaluation; Day 2: 10:00 AM – 3:00 PM Main Evaluation | Auditorium, MBA Block | Agentic AI Hackathon | 3 - 5 | YES ( PPT + EXPLANATION + INTRO VIDEO IN FORM ) | total 50+ teams compete for the win together...their topics and themes are already revealed dyring mid evaluation all they have is 24hrs to build their ideas and make the mvp or the full product there is another mid evaluation round on first day which elemenats 50% teams and only top 50% teams remains in the hackathon and on final evaluation they are evaluated based on many criterias but most important winning criterias are regional language support , best ui , offline compatibily , type of agentic framework ( deterministic or autonomous ) as its a AGENTIC AI Hackathon | NEXTECH 2.0 - AGENTS ASSEMBLE | 2026-06-04 |  | SHRIYANSH DASH , OM PRAKASH NAHAK , AMAN SINGH | 20 | Top 50 teams; 3–5 participants per team (150–250 participants maximum if all teams are full) | ₹500 per team, only after selection | 1st prize- 20000 , 2nd prize- 15000 , 3rd prize- 10000 TOTAL PRIZE POOL - 45000 | Software / AI / Innovation | Flagship two-day build event focused on EdTech and regional-language accessibility, with teams designing, developing and demonstrating technology solutions. | Dedicated workstations; minimum 2 power sockets per participant; redundant high-speed Wi-Fi with high concurrency; GitHub repository and submission workflow; dedicated evaluation zone; technical support. | Tables and ergonomic chairs for 50 teams; catering area; approved overnight facility management/security; evaluation area. | Participant ID Card; Lanyard/participant identification material; Pen; Notebook; Sticker Sheet; Participant Badge if finalized; Event Schedule; Rules & Regulations; GitHub Submission Instructions; Food Tokens | Aadhaar ID Card; College ID Card; Approval Letter; Selection / Confirmation Mail | Event Management; Technical & Network; Registration & Desk; Evaluation & Judging; Hospitality & Refreshments; Discipline & Safety; Marketing, Media & Design | Mid Evaluation: 30% on 10 Oct, 4:00–7:00 PM. Main Evaluation: 70% on 11 Oct, 10:00 AM–3:00 PM. Evaluation includes problem understanding, innovation, technical implementation, functionality, regional language support, offline capability, agentic implementation, UX, impact and presentation. | Event Registration Sheet; Final Selected Team List; Mid Evaluation Sheets; Main Evaluation Sheets; GitHub submission records | External judging panel, exact judge count, venue, final rulebook and agentic-framework requirement are pending confirmation.

## Volunteers & Faculty
EVENT NAMES | CATAGORY
| FACULTY | Internal Judge | EVENT LEAD | GUEST INCHARGE | REGISTRATION | HOSPITALITY | GENERAL VOLUNTEER
INAUGURATION - 20 |  |  | 2 | 6 |  | 6 | 6
| FACULTY | Internal Judge | EVENT LEAD | GUEST INCHARGE | REGISTRATION | HOSPITALITY | GENERAL VOLUNTEER
DRONE OBSTACLE - 20 | 3 | 1 | 2 | 2 | 4 | 4 | 8
| Sanjay Ray | Santosh Sahu
Santosh Sahu
J Binita
| FACULTY | Internal Judge | EVENT LEAD | GUEST INCHARGE | REGISTRATION | HOSPITALITY | GENERAL VOLUNTEER
CANVAS PAINTING - 22 | 3 |  | 2 | 2 | 4 | 4 | 10
Madhubrata Dash
Sambit Sethy
Swarnaprava Sahoo
| FACULTY | Internal Judge | EVENT LEAD | GUEST INCHARGE | REGISTRATION | HOSPITALITY | GENERAL VOLUNTEER
IOT DISPLAY - 17 | 3 |  | 2 | 2 | 3 | 4 | 6
Jitendra Padhi
Pranay Rout
Bhagyalaxmi Ma'am
| FACULTY | Internal Judge | EVENT LEAD | GUEST INCHARGE | REGISTRATION | HOSPITALITY | GENERAL VOLUNTEER
PANEL - 14 |  |  | 2 | 2 | 2 | 4 | 4
| FACULTY | Internal Judge | EVENT LEAD | GUEST INCHARGE | REGISTRATION | HOSPITALITY | GENERAL VOLUNTEER
TECHNO DANCE - 33 | 3 | 1 | 2 | 4 | 6 | 6 | 15
| Saroj Sir | Saroj Sir
Sushree Sucharita Kar
| FACULTY | Internal Judge | EVENT LEAD | GUEST INCHARGE | REGISTRATION | HOSPITALITY | GENERAL VOLUNTEER
IDEATHON - 24 | 3 | 1 | 2 | 2 | 4 | 6 | 10
| Jaswant Patra | Jaswant Patra
| FACULTY | Internal Judge | EVENT LEAD | GUEST INCHARGE | REGISTRATION | HOSPITALITY | GENERAL VOLUNTEER
TECH QUIZ - 20 | 3 | 1 | 2 | 2 | 4 | 4 | 8
| Chanchal Mukharjee | Chanchal Mukharjee
Sangram Behera
| FACULTY | Internal Judge | EVENT LEAD | GUEST INCHARGE | REGISTRATION | HOSPITALITY | GENERAL VOLUNTEER
SEMINAR - 16 |  |  | 2 | 2 | 2 | 4 | 6
| FACULTY | Internal Judge | EVENT LEAD | GUEST INCHARGE | REGISTRATION | HOSPITALITY | GENERAL VOLUNTEER
FREE-FIRE GAMING | 3 | 1 | 2 | 1 | 6 | 6 | 10
Rashmi Sir

## Volunteer List
Event Name - Drone Obstacle Course, Date - 07/10/2026, Time - 08:00 to 13:00
Faculty Assigned - Santosh Sahu • J. Binita • Sanjay Ray
SL. NO | NAME | STREAM | BRANCH | YEAR | MOBILE NO.
LEADER
1 | PARTHA SARATHI NAYAK | MBA | MBA | 3RD | 9692767042
2 | ADISAKTI SAHOO | BTECH | CSE | 3RD | 6370656719
VOLUNTEERS (15)
1 | Subhalaxmi Dash | B TECH | CSE | 5TH | 7978858262
2 | RUPIKA P.KUMARI | BTECH | CSE | 2ND | 96412 49094
3 | SACHITRA KUMAR JENA | BTECH | CSE | 7TH | 9827022918
4 | DHABALESWAR JENA | BTECH | CSE | 7TH | 9827729375
5 | Om Pragya | BTECH | ECE | 3RD | 6370209139
6 | Subhashree Malla | B.TECH | CSE | 5TH | 8260980781
7 | KARTIK SHRAMA | BCA | BCA | 4TH | 6371003394
8 | PRIYA MISHRA | BTECH | CSE | 3RD | 9508337405
9 | BARSHA BANDITA NAYAK | BCA | BCA | 4TH | 9777406295
10 | RANJIT SETHI | B.TECH | MECH | 3RD | 7815040041
11 | SOLONI PRIYADARSHINI SAHU | B.TECH | CSE | 1ST | 9078980859
12 | Alisha Chakraborty | BTECH |  | 1ST | 9348765391
13 | SATYAJIT DASH | BTECH | CSE | 3RD | 6370632833
14 | Tanukrishna Das | BTECH | CSE | 3RD | 7205164393
15 | ADITYA BARIK | BTECH | CIVIL | 3RD | 7008158411
16 | ARUN APAT | BTECH | ECE | 3RD | 7846963591
Event Name - Canvas Painting, Date - 07/10/2026, Time - 10:00 to 13:00
Faculty Assigned - Madhubrata Dash • Sambit Sethy • Swarnaprava Sahoo
SL. NO | NAME | STREAM | BRANCH | SEMESTER | MOBILE NO.
LEADER
1 | Sanjeevani Panda | BTECH | CSE | 3RD | 9692196970
2 | Shyan | DIPLOMA | CSE |  | 9337316813
VOLUNTEERS (10)
1 | SUDEEPA SENAPATI | BCA | BCA | 4TH | 6372514745
2 | NARENDRA DASH | B.TECH | EEE | 1ST | 9692225331
3 | TANMAYA BANCHORE | BTECH | ECE | 3RD | 8658486171
4 | ANKEETA MOHANTY | BTECH | CSE | 5TH | 9827869350
5 | CHANDRASEKHAR NAYAK | B.TECH | CSE | 3RD | 9040116491
6 | Bhagyasmita Samal | BTECH | CSE | 4TH | 7847063030
7 | RAJESH KUMAR PATRA | BCA | BCA | 2ND | 9827361940
8 | PRIYANKA PAIKARAY | B. Tech | CSE | 3rd | 6371513826
9 | SAHANUMA FIRDOSH | B.TECH | CSE | 7TH | 9827112248
10 | Subhashree Lenka | BTECH |  | 1ST | 7008892315
11 | Tanushree Sahoo | BTECH |  | 1ST | 7205777369
12 | BARSA BANDITA NAYAK | BCA | BCA | 4TH | 9777406295
13 | SOUMYA RANJAN SETHI | BTECH | CSE | 7TH | 8249919119
Event Name - Technical Poster Presentation, Date - 07/10/2026, Time - 10:00 to 13:00
Faculty Assigned -
SL. NO | NAME | STREAM | BRANCH | SEMESTER | MOBILE NO.
LEADER
1 | Ankita Mohanty | B.TECH | CSE | 3RD | 98278 69350
2 | Priyabrata Muduli | MBA | MBA | 2ND | 9019125127
VOLUNTEERS (10)
1 | RAJESH PATRA | BCA | BCA | 2ND | 9827361940
3 | MANORANJAN PATRA | B.TECH | MECH | 1ST | 8260770451
4 | Pabitra Ranjan Ray | B.Tech | CSE | 3RD | 7326998497
5 | Binilata Sahoo | BTECH | CSE | 3RD | 7788862057
6 | ASUTOSH CHAINI | B.TECH | CSE | 3RD | 8658688375
7 | Mamali Sahoo | B.Tech | CSE | 3RD | 7684831499
8 | Shagun Pri. Rana | BTECH |  | 1ST | 9078346242
9 | Shradhanjali Rout | BTECH |  | 2ND | 7894633469
Event Name - IoT Display, Date - 07/10/2026, Time - 14:00 to 17:00
Faculty Assigned - JITENDRA PADHI(8895781339) • BHAGYALAXMI DEVI (8249858397) • PRANAY ROUT(8249524153)
SL. NO | NAME | STREAM | BRANCH | SEMESTER | MOBILE NO.
LEADER
1 | SUBHASREE PANDA | B.TECH | CSE | 7TH | 9123987837
2 | VASWATI P MOHANTY | B.TECH | CSE | 7TH | 7608911996
3 | JAGA DAS | BCA | BCA | 4TH | 8984726731
VOLUNTEERS (10)
1 | Pradeep kumar Barik | BTECH |  | 1ST | 7205011679
2 | Atul Kumar Pandey | BTECH |  | 1ST | 9778956825
3 | SUBHRANSHU NAYAK | B.TECH | CSE | 5TH | 8144696447
4 | SANDEEP DAS | BTECH | CSE | 3RD | 7853952594
5 | SUNITA KISHAN | B.TECH | CSE | 4TH | 6372638560
6 | PAYAL PRIYADARSHINI SAMAL | B.TECH | CSE | 1ST | 6372385211
7 | ASHIRBAD MALLIK | B.TECH | CSE | 5TH | 7077022102
8 | Himanshu Padhi | BCA | BCA | 1ST | 6370430018
9 | TANUKRISNA PRIYADARSHINI DAS | B.TECH | CSE | 5TH | 7205164393
10 | RAJESH KUMAR SWAIN | BCA | BCA | 4TH | 9937506763
11 | DINESH PRUSTY | B.TECH | CSE | 4TH | 9827729375
12 | PABITRA RANJAN ROY | B.TECH | CSE | 3RD | 7326998497
Event Name - AD Mad Show, Date - 07/10/2026, Time - 15:00 to 17:00
Faculty Assigned - Subhasmita Mam • Nilima Mam
SL. NO | NAME | STREAM | BRANCH | SEMESTER | MOBILE NO.
LEADER
1 | Asutosh Ranjan Sethy | MBA | MBA |  | 6372955246
VOLUNTEERS (10)
1 | BINA PRADHAN | BCA |  | 4TH | 7894432921
2 | SUPRIYA BEHERA | B.TECH | CSE | 7TH | 9692684810
3 | Ashirbad Mallick | B.Tech | CSE | 3RD | 7077022102
4 | BABUSAN MALLIK | BTECH | CSE | 7TH | 8455856191
5 | Subhalaxmi Patra | MBA |  |  | 8260056369
6 | TARINI PRASAD MOHANTY | MBA | MBA | 2ND | 9861623716
7 | BADRINARAYAN NAYAK | BCA | BCA | 2nd | 7848814501
8 | RAJEEB ROUT | B.TECH | CSE | 5TH | 9861115753
9 | ASHUTOSH CHAINI | B.TECH | CSE | 3RD | 8658688375
10 | Priyabrata Sahoo | BTECH |  | 1ST | 6373805357
Event Name - Panel Discussion, Date - 07/10/2026, Time - 15:00 to 17:00
Faculty Assigned - Kashinath Pati • Sambit Sethi • Barsha Priyadarshinee
SL. NO | NAME | STREAM | BRANCH | SEMESTER | MOBILE NO.
LEADER
1 | Sagar Nayak | BCA | BCA | 4th | 9337932696
2 | SANJAY SAHOO | MBA | MBA | 2ND | 7849018797
VOLUNTEERS (6)
1 | Manoranjan Duhan | BTECH |  | 1ST | 9827629041
2 | P. Amritya Charan | MBA | MBA | 2ND | 8480264099
3 | Malaya Rout | MBA | MBA |  | 9078415812
4 | SUSIL SUMAN DHAL | MBA | MBA | 2ND | 6370558741
5 | Pallavi Priyadarshini | MBA | MBA |  | 9827700159
6 | Guru Prasad Malick | B.Tech | CSE | 2ND | 7853071310
Event Name - CXO Round Table, Date - 08/10/2026, Time - 10:00 to 13:00
Faculty Assigned - Akankhya Mam
SL. NO | NAME | STREAM | BRANCH | SEMESTER | MOBILE NO.
LEADER
1 | Tushar Dhal (MBA) | MBA |  | 4th | 9078634571
VOLUNTEERS (10)
1 | Subhalaxmi Dash | B TECH | CSE | 5TH | 7978858262
2 | RUPIKA P.KUMARI | BTECH | CSE | 2ND | 9641249094
3 | SACHITRA KUMAR JENA | BTECH | CSE | 7TH | 9827022918
4 | DHABALESWAR JENA | BTECH | CSE | 7TH | 9827729375
5 | Om Pragya | BTECH | ECE | 3RD | 6370209139
6 | Subhashree Malla | B.TECH | CSE | 5TH | 8260980781
7 | KARTIK SHRAMA | BCA | BCA | 4TH | 6371003394
8 | PRIYA MISHRA | BTECH | CSE | 3RD | 9508337405
9 | BARSHA BANDITA NAYAK | BCA | BCA | 4TH | 9777406295
10 | RANJIT SETHI | B.TECH | MECH | 3RD | 7815040041
11 | SOLONI PRIYADARSHINI SAHU | B.TECH | CSE | 1ST | 9078980859
Event Name - Tech Biz Quiz, Date - 08/10/2026, Time - 10:00 to 12:00
Faculty Assigned - Chanchal Mukherjee • Neeha Pradhani • Sangram Behera
SL. NO | NAME | STREAM | BRANCH | SEMESTER | MOBILE NO.
LEADER
1 | DIBYANSHU NAYAK | B.TECH | MECH | 4TH | 7077188155
2 | TAPASWINI MISHRA | BTECH | CSE | 3RD | 9861296488
3 | PRABHUDUTTA MOHANTY | MBA | MBA |  | 8260948235
VOLUNTEERS (10)
1 | Alisha Chakraborty | BTECH |  | 1ST | 9348765391
2 | SATYAJIT DASH | BTECH | CSE | 3RD | 6370632833
3 | Tanukrishna Das | BTECH | CSE | 3RD | 7205164393
4 | ADITYA BARIK | BTECH | CIVIL | 3RD | 7008158411
5 | ARUN APAT | BTECH | ECE | 3RD | 7846963591
6 | SUDEEPA SENAPATI | BCA | BCA | 4TH | 6372514745
7 | NARENDRA DASH | B.TECH | EEE | 1ST | 9692225331
8 | TANMAYA BANCHORE | BTECH | ECE | 3RD | 8658486171
9 | ANKEETA MOHANTY | BTECH | CSE | 5TH | 9827869350
Event Name - Techno Dance, Date - 08/10/2026, Time - 10:00 to 20:00
Faculty Assigned - Saroj Sir • Sushree Suchitra Kar
SL. NO | NAME | STREAM | BRANCH | SEMESTER | MOBILE NO.
LEADER
1 | Rachita Das | B.Tech | CSE | 3RD | 8984391077
2 | Subhranshu Sekhar Jena | MBA | MBA | 2ND | 8093569907
VOLUNTEERS (15)
1 | CHANDRASEKHAR NAYAK | B.TECH | CSE | 3RD | 9040116491
2 | Bhagyasmita Samal | BTECH | CSE | 4TH | 7847063030
3 | RAJESH KUMAR PATRA | BCA | BCA | 2ND | 9827361940
4 | PRIYANKA PAIKARAY | B. Tech | CSE | 3rd | 6371513826
5 | SAHANUMA FIRDOSH | B.TECH | CSE | 7TH | 9827112248
6 | Subhashree Lenka | BTECH |  | 1ST | 7008892315
7 | Tanushree Sahoo | BTECH |  | 1ST | 7205777369
8 | BARSA BANDITA NAYAK | BCA | BCA | 4TH | 9777406295
9 | SOUMYA RANJAN SETHI | BTECH | CSE | 7TH | 8249919119
10 | RAJESH PATRA | BCA | BCA | 2ND | 9827361940
11 | MANORANJAN PATRA | B.TECH | MECH | 1ST | 8260770451
12 | Pabitra Ranjan Ray | B.Tech | CSE | 3RD | 7326998497
13 | Binilata Sahoo | BTECH | CSE | 3RD | 7788862057
14 | ASUTOSH CHAINI | B.TECH | CSE | 3RD | 8658688375
Event Name - Ideathon, Date - 08/10/2026, Time - 13:00 to 17:00
Faculty Assigned - Jaswant
SL. NO | NAME | STREAM | BRANCH | SEMESTER | MOBILE NO.
LEADER
1 | GAYATRI ROUT | BTECH | CSE | 5TH | 93370 88946
2 | DHANANJAYA SATHPATHY | MBA | MBA | 3RD | 9114784837
VOLUNTEERS (10)
1 | Mamali Sahoo | B.Tech | CSE | 3RD | 7684831499
2 | Shagun Pri. Rana | BTECH |  | 1ST | 9078346242
3 | Shradhanjali Rout | BTECH |  | 2ND | 7894633469
4 | Pradeep kumar Barik | BTECH |  | 1ST | 7205011679
5 | Atul Kumar Pandey | BTECH |  | 1ST | 9778956825
6 | SUBHRANSHU NAYAK | B.TECH | CSE | 5TH | 8144696447
7 | SANDEEP DAS | BTECH | CSE | 3RD | 7853952594
8 | SUNITA KISHAN | B.TECH | CSE | 4TH | 6372638560
9 | PAYAL PRIYADARSHINI SAMAL | B.TECH | CSE | 1ST | 6372385211
10 | ASHIRBAD MALLIK | B.TECH | CSE | 5TH | 7077022102
11 | Himanshu Padhi | BCA | BCA | 1ST | 6370430018
12 | TANUKRISNA PRIYADARSHINI DAS | B.TECH | CSE | 5TH | 7205164393
13 | RAJESH KUMAR SWAIN | BCA | BCA | 4TH | 9937506763
14 | DINESH PRUSTY | B.TECH | CSE | 4TH | 9827729375
Event Name - Expert Talk / Seminar, Date - 08/10/2026, Time - 15:00 to 17:00
Faculty Assigned -
SL. NO | NAME | STREAM | BRANCH | SEMESTER | MOBILE NO.
LEADER
1 | DIBYAJIT ROUT | MBA | MBA | 4TH | 8093795416
2 | ADITYA MOHANTY | DIPLOMA | EE | 3RD
VOLUNTEERS (10)
1 | PABITRA RANJAN ROY | B.TECH | CSE | 3RD | 7326998497
2 | BINA PRADHAN | BCA |  | 4TH | 7894432921
3 | SUPRIYA BEHERA | B.TECH | CSE | 7TH | 9692684810
4 | Ashirbad Mallick | B.Tech | CSE | 3RD | 7077022102
5 | BABUSAN MALLIK | BTECH | CSE | 7TH | 8455856191
6 | Subhalaxmi Patra | MBA |  |  | 8260056369
7 | TARINI PRASAD MOHANTY | MBA | MBA | 2ND | 9861623716
8 | BADRINARAYAN NAYAK | BCA | BCA | 2nd | 7848814501
9 | RAJEEB ROUT | B.TECH | CSE | 5TH | 9861115753
10 | ASHUTOSH CHAINI | B.TECH | CSE | 3RD | 8658688375
Event Name - Marketing Maverick, Date - 09/10/2026, Time - 09:00 to 13:00
Faculty Assigned - Nitin Sir • Subhasmita Mam
SL. NO | NAME | STREAM | BRANCH | SEMESTER | MOBILE NO.
LEADER
1 | RITU PRAGYAN PRIYADARSHINI | MBA | MBA | 3RD | 9692727534
2 | DEBJIT MALICK | BTECH | CSE | 5TH | 8658736591
VOLUNTEERS (6)
1 | SATYAJIT DASH | BTECH | CSE | 3RD | 6370632833
2 | Tanukrishna Das | BTECH | CSE | 3RD | 7205164393
3 | ADITYA BARIK | BTECH | CIVIL | 3RD | 7008158411
4 | ARUN APAT | BTECH | ECE | 3RD | 7846963591
5 | SUDEEPA SENAPATI | BCA | BCA | 4TH | 6372514745
6 | NARENDRA DASH | B.TECH | EEE | 1ST | 9692225331
7 | TANMAYA BANCHORE | BTECH | ECE | 3RD | 8658486171
8 | ANKEETA MOHANTY | BTECH | CSE | 5TH | 9827869350
9 | CHANDRASEKHAR NAYAK | B.TECH | CSE | 3RD | 9040116491
Event Name - Face Painting, Date - 09/10/2026, Time - 10:00 to 12:00
Faculty Assigned - Barsha Priyadarshini, Gopabandhu Sahu, Bhagyalaxmi Devi
SL. NO | NAME | STREAM | BRANCH | SEMESTER | MOBILE NO.
LEADER
1 | SWATI PRAGNYA PARIDA | B.TECH | MECH | 5TH | 70080 02456
2 | SUBHRANSU NAYAK | B.TECH | CSE | 5TH | 81446 96447
VOLUNTEERS (10)
1 | Subhalaxmi Dash | B TECH | CSE | 5TH
2 | RUPIKA P.KUMARI | BTECH | CSE | 2ND | 96412 49094
3 | SACHITRA KUMAR JENA | BTECH | CSE | 7TH | 9827022918
4 | DHABALESWAR JENA | BTECH | CSE | 7TH | 9827729375
5 | Om Pragya | BTECH | ECE | 3RD | 6370209139
6 | Subhashree Malla | B.TECH | CSE | 5TH | 8260980781
7 | KARTIK SHRAMA | BCA | BCA | 4TH | 6371003394
8 | PRIYA MISHRA | BTECH | CSE | 3RD | 9508337405
9 | BARSHA BANDITA NAYAK | BCA | BCA | 4TH | 9777406295
10 | RANJIT SETHI | B.TECH | MECH | 3RD | 7815040041
11 | SOLONI PRIYADARSHINI SAHU | B.TECH | CSE | 1ST | 9078980859
12 | Alisha Chakraborty | BTECH |  | 1ST | 9348765391
Event Name - Free Fire Gaming Tournament, Date - 09/10/2026, Time - 15:00 to 17:00
Faculty Assigned - Rashmi Sir
SL. NO | NAME | STREAM | BRANCH | SEMESTER | MOBILE NO.
LEADER
1 | SUKDEV SUNA | BTECH | ECE | 7TH | 8984941510
2 | SUBHAM SING | BTECH | CSE | 7TH | 6372920799
VOLUNTEERS (10)
1 | Bhagyasmita Samal | BTECH | CSE | 4TH | 7847063030
2 | RAJESH KUMAR PATRA | BCA | BCA | 2ND | 9827361940
3 | PRIYANKA PAIKARAY | B. Tech | CSE | 3rd | 6371513826
4 | SAHANUMA FIRDOSH | B.TECH | CSE | 7TH | 9827112248
6 | Subhashree Lenka | BTECH |  | 1ST | 7008892315
7 | Tanushree Sahoo | BTECH |  | 1ST | 7205777369
8 | BARSA BANDITA NAYAK | BCA | BCA | 4TH | 9777406295
9 | SOUMYA RANJAN SETHI | BTECH | CSE | 7TH | 8249919119
10 | RAJESH PATRA | BCA | BCA | 2ND | 9827361940
11 | MANORANJAN PATRA | B.TECH | MECH | 1ST | 8260770451

## Common Requirements
Common Verification Documents | Aadhaar ID Card; College ID Card; Approval Letter; Selection / Confirmation Mail | All events
Event Registration Sheet | Participant Name; Team Name; College / Institution; Contact Information; Event Name; Registration ID; Verification Status; Participant Signature | All events
Selected Team / Participant List | Printed consolidated list for on-site verification; particularly important for limited-seat events, gaming and Hackathon. | All events
Evaluation Sheets | Team/Participant Name and ID; Event Name and Date; evaluation criteria with marks; judge comments; total score; judge name and signature. | All judged events
Common Infrastructure | Registration/help desks; tables/chairs; power extension boards; stable Wi-Fi/LAN; display screens/projectors and AV setups; signage; directional boards; participant banners; evaluation desks and waiting areas. | All events
Volunteer / Committee Categories | Event Management; Technical & Network; Registration & Desk; Evaluation & Judging; Hospitality & Refreshments; Marketing, Media & Design; Discipline & Safety. | Festival-wide pool; event allocation TBD
Judge Count | Exact number of judges is not specified in the proposal. | All events
Event Fee | Hackathon: ₹200 per team after selection. Other events: ₹100 per participant at registration/confirmation. | All events
Theme Status | Final decision between MARVELS (Avengers Universe) and GALACTIC / Space (Sci-Fi Universe) is pending. | All themed events
9 October Activity | Additional Event / Activity is still TBD. Possible activities include workshops, startup/entrepreneurship sessions, guest lecture/panel, pre-hackathon orientation, exhibition or networking. | Not included in Event Master because no actual event name is confirmed
College Invitation Letter | Official invitation addressed to Principal / Director / HOD with event details, dates, venue, competitions, participation and registration information. | All external colleges
Physical Poster Prints | Printed posters for event promotion; Event Name; Date & Venue; Key Events / Competitions; Registration Details; QR Code; Contact Information; Organizer / College Branding | All events and Colleges
Long Banners for Banner Drop | Large-format printed banners for promotional banner drops; Festival / Event Name; Date & Venue; Key Events / Competitions; Registration Details; QR Code; Contact Information; Organizer / College Branding | All major events

## Source Notes
Source | NEXTECH-2.0-Event-Proposal 2.pdf
Important | This spreadsheet preserves the proposal's confirmed details and marks unspecified items as TBD rather than inventing numbers.
Theme | MARVELS and GALACTIC / Space are both proposed; final theme is not yet confirmed.
9 October | No actual event name is confirmed; therefore it is excluded from the event master.